## Project Overview
Project overview
Field | Details
Project Title | Skilling Program for Youth in IT–ITeS Sector
Brief Project Description | A college-cum-community-based training program for 1,980 underserved youth in Hyderabad, Mumbai, and Bangalore. The program will be implemented through 9 colleges and 3 Express Training Centres (ETCs), delivering training in AI Productivity & Applications, followed by certification and placement support. | Location | No. of Colleges | No. of candidates trained in colleges | No. of Express Training Centre (ETC) | No. of candidates trained in ETC | Total No. of Candidates to be trained
Project Funder | Ivanti Technology India Pvt. Ltd. | Bangalore | 3 | 480 | 1 | 180 | 660
Project Entity | Sambhav Foundation | Mumbai | 3 | 480 | 1 | 180 | 660
Theme | Employability | Hyderabad | 3 | 480 | 1 | 180 | 660
Sub Theme | Colleges | Total | 9 | 1440 | 3 | 540 | 1980
MOU Effective Start Date | 1st September 2025 | Express Training Centres (ETC) are temporary, rented training centres equipped with all necessary infrastructure, including computers, where no additional setup is required before commencing training. These centres are ready-to-use and facilitate immediate training delivery.
MOU End Date | 31st March 2026
Project Start Date | 2025-09-01
Project End Date | 2026-03-01
Deployment Region | Mumbai, Bangalore & Hyderabad
Course | AI Productivity & Applications
Expected Outcomes | - 1,980 candidates trained, assessed & certified
- 50% placements post certification (approx. 990 youth)
- 3-month post-placement tracking of placed candidates
Key Deliverables | - Identification & tie-up with 9 colleges and setting up 3 ETCs
- Human Resource Deployment
- Stakeholder Engagement
- Training of Trainers (ToT)
- Content Development
- Awareness, Mobilization & Counselling of the candidates
- Registration, Onboarding & Batch Formation
- Training Delivery
- Assessment & Certification
- Placements & Post-Placement Tracking
- Monitoring & Evaluation
- Program Reporting
Monitoring and Reporting | - Continuous Monitoring & Evaluation (M&E)
- Regular program reporting to Ivanti
- Final program report with outcomes & learnings
Overall Objective | To bridge the skill gap in the economy by enabling access to college- and community-based training for underserved youth, promoting employability in the IT–ITeS sector, and ensuring 50% are linked to job opportunities.

## Activity sheet
Milestone | Activity | Responsibility | Accountability | Consulted | Informed | Frequency | Start date | End date
Human Resource Deployment | Source, interview and hire Human resources as per the requirement (refer "HR Sheet" in the file) | TA | HR | PM, TM, RMG | BU Head, PMT Lead | Once | 2025-09-12 | 2025-09-30
Human Resource Deployment | Orient the project team on the project deliverables, reporting and other complinace requirements | TM | PM | BU Head | PMT Lead | Once | 2025-09-12 | 2025-09-30
Identification of Colleges | Identify & Tie-up with 9 colleges (3 in Mumbai, 3 in Bangalore, 3 in Hyderabad) | TM,Project coordinator | TM |  | PM,BU head | Once | 2025-09-12 | 2025-09-30
Identification of Express Training Centres (ETC) | Identify 1 ETC on rental basis in each location with basic facilities and basic computer system availability. | I&M | I&M | PM, TM, BU Head |  | Once | 2025-09-01 | 2025-09-20
Identification of Express Training Centres (ETC) | Sign the agreement with respective landlord of the centre space and computer system rental | Legal team | I&M | Category Owner - Rent, UC | Finance | Once | 2025-09-21 | 2025-09-30
Content development | Develop the content as per the project requirements | Training | Training |  | TM, PM, BU Head, PMT Lead | Once | 2025-09-12 | 2025-09-30
TOT | Train trainers on content delivery, training methodology and usage of SAHI platform | Training | Training | - | TM, PM | Once | 2025-10-01 | 2025-10-31
Inaugration | Schedule & arrange an inauguration ceremony for launching of the project. Invite key stakeholders including donor representatives, community leaders and Principal and teachers in case of colleges Ensure proper branding during inauguration ceremony | Project Co-ordinator | TM | PM | PMT Lead, BU Head | Once | 2025-10-01 | 2025-10-15
Mobilization | Design Flyers, IEC material,Banners, and Standees. | Marketing | PM | TM, Mobilizer, Project coordinator | BU Head, PMT Lead | Ongoing | 2025-09-15 | 2025-09-20
Mobilization | Print IEC Material,flyers and banners detailing the program, benefits, and registration process for distribution and mobilization purpose | Printing & Stationery | Marketing |  | PM, TM, Mobilizer, CM, BU Head | Ongoing | 2025-09-21 | 2025-09-25
Mobilization | Conduct awareness campaigns- Digital and physical mobilization in colleges & community | Project Coordinator, Mobilizer | TM | Marketing | PM, BU Head, PMT Lead | Ongoing | 2025-09-15 | 2026-03-15
Counselling | Creation of entry assessments and counselling framework | Training | Training | Placement, TM | PM | Once | 2025-09-15 | 2025-09-25
Counselling | Providing counseling to the interested/shortlisted learners | Project Coordinator, Mobilizer | TM | Training | TM, PM, BU Head, PMT Lead | Ongoing | 2025-09-15 | 2026-03-15
Registration & Batch formation | Collect basic data information of candidates and groups. Register candidates on SAHI platform Create batches in SAHI and tag candidates to the batches | Project Coordinator, Mobilizer | TM |  | PM, BU Head, PMT Lead | Ongoing | 2025-09-15 | 2026-03-15
Baseline assessment and endline assessment | Create or prepare impact assessment tools | Impact Team | PM | Sales | TM, BU Head | Once | 2025-09-15 | 2025-09-30
Baseline assessment and endline assessment | Conduct baseline and endline assessment assessments for all registered candidates. | Trainer, Project Coordinator | TM | Impact Team | PM, BU Head, PMT Lead | Baseline-at the start of the batch Endline - at the end of the batch | 2025-09-15 | 2026-03-15
Training | Deliver AI Productivity & Applications (100 hours) course to 1,980 candidates (1,440 in 9 colleges + 540 in 3 ETCs) | Trainer | Training |  | PM, TM, BU Head, PMT Lead | Ongoing | 2025-10-01 | 2026-03-31
Assessments | Identification & finalization of third party assessor | Assessment Team | PM | Training | Project Coordinator, Trainer, TM, BU Head,PMT Lead | Once | 2025-09-15 | 2025-10-15
Assessments | Conduct third party assessment | 3rd party assessor | Trainer | Project coordinator, TM | PM,PMT Lead, Training, BU Head | Ongoing | 2025-10-16 | 2026-03-31
Certification | Design certificate as per project & donor requirements | Marketing | PM | Sales | Printing & Stationery | Once | 2025-09-15 | 2025-10-15
Certification | Take donor approval on certificate design | PM | PM | Sales | PMT Lead, BU Head | Once | 2025-09-15 | 2025-10-15
Certification | Share details of the certificates to be printed with the printing team | Project coordinator | TM | PM | PMT Lead, BU Head | Ongoing | 2025-10-16 | 2026-03-31
Certification | Organize certificate distribution ceremony for all certified candidates | Project coordinator | TM | PM | PMT Lead, BU Head | Ongoing | 2025-10-16 | 2026-03-31
Placement | Identification of work opportunities Collaboration with Employers & Industry Experts | Placement Officer | Placement Officer | Training, TM, BU Head | PMT Lead, PM | Ongoing | 2025-10-16 | 2026-04-20
Placement | Upload employer company details on SAHI platform | Placement Officer | Placement Officer | Project Coordinator | PM, PMT Lead, TM, BU Head | Ongoing | 2025-10-16 | 2026-04-20
Placement | Opportunity preparation for learner | Trainer | Training | Placement Officer | PM, TM, Project Coordinator, BU Head, PMT Lead | Ongoing | 2025-10-16 | 2026-04-20
Placement | Learners interview and deployment Note - Placement must be done batch wise and not at the end of the project. Every month placement numbers to be completed and reported. | Placement Officer | Placement | Trainers | PM, PMT Lead, TM, BU Head | Ongoing | 2025-10-16 | 2026-04-20
Placemnt tracking | Placement Tracking for 3 months | MIS | MIS | Placement Officer | PM,TM,BU head, PMT Lead | 3 months post placement for each placed candidate | 2025-12-16 | 2026-07-16
Monitoring & Evaluation | Regular monitoring of enrolment, training quality, placement outcomes; arrange reviews & document findings | PM | PM | TM, Project coordinator, Trainer | BU Head, PMT Lead | Ongoing | 2025-09-12 | 2026-04-30
Testimonials | -Collect at least three successful testimonials for each batch -High quality video and text testimonials to be submitted to donor on a quarterly basis. | Trainer, Project Coordinator | PM | Marketing | TM, BU Head, PMT Lead | Batch wise | 2025-10-16 | 2026-03-31
Social Media Marketing & Communication | Creation and Sharing of Social Media Posts | Marketing | Marketing | PM | BU head,TM, PMT Lead | Monthly | 2025-09-15 | 2026-03-31
Volunteer Activity by Employees | Coordinate with Ivanti employees, fix date & time, arrange sessions (guest lectures, mock interviews, mentoring) | Volunteering Executive | PM | TM, Project coordinator | BU Head, PMT Lead, | Quarterly | 2025-10-01 | 2026-03-31
Program Reporting | Project activity progress report to be shared with donor once a month. Including monthly MIS, narrative report, pictures, videos, etc with details of progress achieved. | PM | PM | Project Coordinator, TM, BU Head, PMT Lead | Sales | Monthly | 2025-10-01 | 2026-03-31
UC Submission | Submission of project fund utilization statement quarterly | UC team | UC team | PM, TM | BU Head, sales | Monthly | 2025-10-01 | 2026-03-31
UC Submission | Audited financial UC to be submitted at the end of the year | UC | PM | PMT Lead, BU Head | Sales | Annually | 2026-03-15 | 2026-03-31
Impact Report and video | Impact report preparation with key achievements and impact stories at the end of each year and end of project | Knowledge Partner | PM | BU Head, Sales | Sales | Once | 2026-03-15 | 2026-03-31

## HR sheet
Role | full time/shared | Location | Requirements | no of months(year 1) | Description | Responsibilities
Program Coordinator | Full time | Bangalore | 1 | 7 | Program Coordinator will coordinate with partner colleges, manage the Express Training Center, and ensure smooth execution of training batches. The coordinator will act as a link between trainers, mobilizers, and other stakeholders, ensuring that program activities are executed efficiently and in line with MoU requirements. | - Liaise with colleges to facilitate student enrollment and ensure smooth collaboration for the training program - Coordinate with trainers, mobilizers, and other stakeholders to ensure smooth implementation of training programs - Manage batch formation, track participant progress, and monitor learning outcomes. - Oversee operations of the Express Training Center, ensuring proper scheduling, resources, and training delivery.
|  | Hyderabad | 1 | 7
|  | Mumbai | 1 | 7
Placement officer | Shared | Bangalore | 1 | 7 | Placement Officers are responsible for linking trained candidates with employment opportunities in the IT–ITeS sector. They build relationships with employers, organize placement drives, prepare candidates through CV building and mock interviews, and track post-placement outcomes for three months. | A dedicated officer for candidate placement process (From Batch Initiation till April for placements spillover)
|  | Hyderabad | 1 | 7
|  | Mumbai | 1 | 7
Trainer | Full time | Bangalore | 4 | 6 | Trainers are responsible for delivering the AI Productivity & Applications course (100 hours) under the IT–ITeS skilling program. They act as the primary facilitators of learning, ensuring candidates acquire both technical and employability skills as per industry standards. Trainers bridge classroom instruction with practical applications, preparing students for assessment, certification, and eventual placement. | Deliver the AI Productivity & Applications training (100 hours) to final-year graduates, ensure active participation, maintain attendance, prepare candidates for assessments, and support their skill development for IT–ITeS sector placements. 1 trainer for each college and one for ETC
|  | Hyderabad | 4 | 6
|  | Mumbai | 4 | 6
Mobilizer | Full time | Bangalore | 1 | 7 | Mobilizers are the first point of contact between the program and the community. They create awareness about the IT–ITeS skilling program, identify eligible final-year graduate youth from local communities, and guide them through the enrolment process. Mobilizers ensure outreach, documentation, and candidate readiness for counselling and training. | Identify and mobilize eligible youth from communities, conduct outreach and awareness activities, support enrolment and SAHI portal entry, and ensure candidates attend counselling and join the IT–ITeS training program.
|  | Hyderabad | 1 | 7
|  | Mumbai | 1 | 7

## Course Details
Particulars | Details
Job Role | AI Productivity & Applications
Sector | IT-ITeS
Minimum Qualifications | Final year Graduate Students
Training Duration | 100 Hours
Course Module | The following modules will be covered during the Program:
· Introduction the Course
· Portfolio Building for Digi locker
· Introduction to AI in the Workplace
· Communication & Customer Handling and Employability Skills
· Introduction to Computer Basics and Typing Skills
· AI tools for Daily Tasks
· Content Creation with AI
· Using AI in Office Tools
· Time Management and Productivity
· Data and Reporting
· Professional Soft Skills
· AI Ethics and Data Privacy

## Mobilization Table
Checklist Item | Details (as per MoU/Proposal) | Verification Document | Status (Completed / Pending)
Gender | Record gender details for program reporting | ID proof / Self-declaration
Educational Qualification | Candidate must be a final-year graduate (any stream), eligible for IT–ITeS skilling program – AI Productivity & Applications | College ID card / Bonafide certificate / Marksheets
Residential Proof | Candidate residence must be within program deployment regions (Mumbai, Bangalore, Hyderabad) | Aadhar Card / Ration Card / Utility Bill
Candidate Personal Details | Collect name, contact info, emergency details | Application Form
Beneficiary Background Verification | Capture socio-economic details for baseline & reporting | Counselling Form
Counselling | Provide orientation on IT–ITeS training program (100 hours), explain benefits & career outcomes | Counseling Attendance Sheet
Mobilization & Outreach | Conduct awareness sessions in 9 colleges + 3 ETCs | Photos, Attendance Sheets
Selection, Screening & Enrollment | Screen eligible candidates, finalize enrollment, allocate batches | Enrollment List
SAHI Portal Entry | Enter all enrolled candidate data into SAHI App for tracking | SAHI Portal Entry Screenshot
Acknowledgment of Receipt | Provide enrollment acknowledgment to candidate | Enrollment Acknowledgment Slip
Acknowledgment of Receipt | Provide acknowledgment / receipt of enrollment to candidate | Enrollment Acknowledgment Slip

## Marketing
Activity | Category (B2B / B2C) | Details | Execution Methods | Frequency
Program Launch Announcement | B2B + B2C | Publicize program inauguration and partnership between Ivanti & Sambhav | Press release, LinkedIn posts, Sambhav & Ivanti websites, media coverage | Once (at launch)
College Awareness Sessions | B2C | Drive awareness among final-year students in 9 colleges | On-campus events, posters, WhatsApp groups, student clubs | Before each batch cycle
Community Outreach | B2C | Mobilize youth for ETC enrolments | Pamphlets, local community meetings, WhatsApp campaigns, social media ads | Ongoing (monthly)
Employer Engagement | B2B | Position program with employers for placements and internships | Employer roundtables, LinkedIn posts, direct outreach | Quarterly
Volunteer Engagement Stories | B2B | Showcase Ivanti employee involvement in guest lectures & inaugurations | LinkedIn, newsletters, Ivanti internal communications | Ongoing (per activity)
Success Stories (Students) | B2C | Highlight trained and placed youth to inspire others | Short videos, Instagram/Facebook posts, reels, LinkedIn case studies | Monthly
Placement Drives Promotion | B2B + B2C | Attract companies and highlight candidate readiness | Flyers, LinkedIn posts, email campaigns to employers | Before every placement drive
Impact Reporting (CSR Branding) | B2B | Share outcomes with corporate and CSR stakeholders | CSR reports, LinkedIn articles, Ivanti & Sambhav newsletters | Bi-annual (midline, endline)

## Batch Plan
Project name | Location | Center name | Course Name | CRT start date | CRT end date | Revised CRT start Date | Revised CRT End Date | OJT start date | OJT end date | Mobilization start date | Mobilization end date | Mobilization target | Enrollment start date | Enrollment end date | Enrollment target | Certification start date | Certification end date | Certification target | Placement start date | Placement end date | Placement target | Batch created (Yes/No)
Ivanti Tech | Bangalore | College 1 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Bangalore | College 1 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Bangalore | College 1 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Bangalore | College 1 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Bangalore | College 2 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Bangalore | College 2 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Bangalore | College 2 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Bangalore | College 2 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Bangalore | College 3 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Bangalore | College 3 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Bangalore | College 3 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Bangalore | College 3 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Bangalore | ETC | AI Productivity & Applications | 2025-10-15 | 2025-11-14 |  |  | - | - | 2025-09-30 | 2025-10-10 | 35 | 2025-10-11 | 2025-10-14 | 33 | 2025-11-11 | 2025-11-14 | 30 | 2025-11-15 | 2025-11-30 | 15
Ivanti Tech | Bangalore | ETC | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 35 | 2025-10-28 | 2025-10-31 | 33 | 2025-11-28 | 2025-12-01 | 30 | 2025-12-02 | 2025-12-17 | 15
Ivanti Tech | Bangalore | ETC | AI Productivity & Applications | 2025-11-15 | 2025-12-15 |  |  | - | - | 2025-10-31 | 2025-11-10 | 35 | 2025-11-11 | 2025-11-14 | 33 | 2025-12-12 | 2025-12-15 | 30 | 2025-12-16 | 2025-12-31 | 15
Ivanti Tech | Bangalore | ETC | AI Productivity & Applications | 2025-12-02 | 2026-01-01 |  |  | - | - | 2025-11-17 | 2025-11-27 | 35 | 2025-11-28 | 2025-12-01 | 33 | 2025-12-29 | 2026-01-01 | 30 | 2026-01-02 | 2026-01-17 | 15
Ivanti Tech | Bangalore | ETC | AI Productivity & Applications | 2025-12-15 | 2026-01-14 |  |  | - | - | 2025-11-30 | 2025-12-10 | 35 | 2025-12-11 | 2025-12-14 | 33 | 2026-01-11 | 2026-01-14 | 30 | 2026-01-15 | 2026-01-30 | 15
Ivanti Tech | Bangalore | ETC | AI Productivity & Applications | 2026-01-02 | 2026-02-01 |  |  | - | - | 2025-12-18 | 2025-12-28 | 35 | 2025-12-29 | 2026-01-01 | 33 | 2026-01-29 | 2026-02-01 | 30 | 2026-02-02 | 2026-02-17 | 15
Ivanti Tech | Mumbai | College 1 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Mumbai | College 1 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Mumbai | College 1 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Mumbai | College 1 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Mumbai | College 2 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Mumbai | College 2 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Mumbai | College 2 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Mumbai | College 2 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Mumbai | College 3 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Mumbai | College 3 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Mumbai | College 3 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Mumbai | College 3 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Mumbai | ETC | AI Productivity & Applications | 2025-10-15 | 2025-11-14 |  |  | - | - | 2025-09-30 | 2025-10-10 | 35 | 2025-10-11 | 2025-10-14 | 33 | 2025-11-11 | 2025-11-14 | 30 | 2025-11-15 | 2025-11-30 | 15
Ivanti Tech | Mumbai | ETC | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 35 | 2025-10-28 | 2025-10-31 | 33 | 2025-11-28 | 2025-12-01 | 30 | 2025-12-02 | 2025-12-17 | 15
Ivanti Tech | Mumbai | ETC | AI Productivity & Applications | 2025-11-15 | 2025-12-15 |  |  | - | - | 2025-10-31 | 2025-11-10 | 35 | 2025-11-11 | 2025-11-14 | 33 | 2025-12-12 | 2025-12-15 | 30 | 2025-12-16 | 2025-12-31 | 15
Ivanti Tech | Mumbai | ETC | AI Productivity & Applications | 2025-12-02 | 2026-01-01 |  |  | - | - | 2025-11-17 | 2025-11-27 | 35 | 2025-11-28 | 2025-12-01 | 33 | 2025-12-29 | 2026-01-01 | 30 | 2026-01-02 | 2026-01-17 | 15
Ivanti Tech | Mumbai | ETC | AI Productivity & Applications | 2025-12-15 | 2026-01-14 |  |  | - | - | 2025-11-30 | 2025-12-10 | 35 | 2025-12-11 | 2025-12-14 | 33 | 2026-01-11 | 2026-01-14 | 30 | 2026-01-15 | 2026-01-30 | 15
Ivanti Tech | Mumbai | ETC | AI Productivity & Applications | 2026-01-02 | 2026-02-01 |  |  | - | - | 2025-12-18 | 2025-12-28 | 35 | 2025-12-29 | 2026-01-01 | 33 | 2026-01-29 | 2026-02-01 | 30 | 2026-02-02 | 2026-02-17 | 15
Ivanti Tech | Hyderabad | College 1 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Hyderabad | College 1 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Hyderabad | College 1 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Hyderabad | College 1 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Hyderabad | College 2 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Hyderabad | College 2 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Hyderabad | College 2 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Hyderabad | College 2 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Hyderabad | College 3 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Hyderabad | College 3 | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 45 | 2025-10-28 | 2025-10-31 | 43 | 2025-11-28 | 2025-12-01 | 40 | 2025-12-02 | 2025-12-17 | 20
Ivanti Tech | Hyderabad | College 3 | AI Productivity & Applications | 2025-12-01 | 2025-12-31 |  |  | - | - | 2025-11-16 | 2025-11-26 | 45 | 2025-11-27 | 2025-11-30 | 43 | 2025-12-28 | 2025-12-31 | 40 | 2026-01-01 | 2026-01-16 | 20
Ivanti Tech | Hyderabad | College 3 | AI Productivity & Applications | 2026-01-01 | 2026-01-31 |  |  | - | - | 2025-12-17 | 2025-12-27 | 45 | 2025-12-28 | 2025-12-31 | 43 | 2026-01-28 | 2026-01-31 | 40 | 2026-02-01 | 2026-02-16 | 20
Ivanti Tech | Hyderabad | ETC | AI Productivity & Applications | 2025-10-15 | 2025-11-14 |  |  | - | - | 2025-09-30 | 2025-10-10 | 35 | 2025-10-11 | 2025-10-14 | 33 | 2025-11-11 | 2025-11-14 | 30 | 2025-11-15 | 2025-11-30 | 15
Ivanti Tech | Hyderabad | ETC | AI Productivity & Applications | 2025-11-01 | 2025-12-01 |  |  | - | - | 2025-10-17 | 2025-10-27 | 35 | 2025-10-28 | 2025-10-31 | 33 | 2025-11-28 | 2025-12-01 | 30 | 2025-12-02 | 2025-12-17 | 15
Ivanti Tech | Hyderabad | ETC | AI Productivity & Applications | 2025-11-15 | 2025-12-15 |  |  | - | - | 2025-10-31 | 2025-11-10 | 35 | 2025-11-11 | 2025-11-14 | 33 | 2025-12-12 | 2025-12-15 | 30 | 2025-12-16 | 2025-12-31 | 15
Ivanti Tech | Hyderabad | ETC | AI Productivity & Applications | 2025-12-02 | 2026-01-01 |  |  | - | - | 2025-11-17 | 2025-11-27 | 35 | 2025-11-28 | 2025-12-01 | 33 | 2025-12-29 | 2026-01-01 | 30 | 2026-01-02 | 2026-01-17 | 15
Ivanti Tech | Hyderabad | ETC | AI Productivity & Applications | 2025-12-15 | 2026-01-14 |  |  | - | - | 2025-11-30 | 2025-12-10 | 35 | 2025-12-11 | 2025-12-14 | 33 | 2026-01-11 | 2026-01-14 | 30 | 2026-01-15 | 2026-01-30 | 15
Ivanti Tech | Hyderabad | ETC | AI Productivity & Applications | 2026-01-02 | 2026-02-01 |  |  | - | - | 2025-12-18 | 2025-12-28 | 35 | 2025-12-29 | 2026-01-01 | 33 | 2026-01-29 | 2026-02-01 | 30 | 2026-02-02 | 2026-02-17 | 15
Formulas:
CRT end date = [CRT start date]+30
Mobilization start date = [CRT start date]-15
Mobilization end date = [CRT start date]-5
Enrollment start date = [Mobilization end date]+1
Enrollment end date = [CRT start date]-1
Certification start date = [CRT end date]-3
Certification end date = [CRT end date]
Placement start date = [Certification end date]+1
Placement end date = [Placement start date]+15