## Sheet1
Contract ID | Entity | Expected Collection - FY | Project name | Project ID | Donor Name | Total Project Value | FY24-25 project value | milestone % of project value | Payment Milestone/Document requirement Description | Type of payment | Expected Date/Month of Billing | Billing Value | LE Date/Month of Billing | Actual Date of Billing | Actual Amount of Billing | Invoice/GR No. | Expected Date/Month of Collection | LE Month of Collection | LE Month of Collection2 | Status of Collection | Actual Date of Collection | Actual Collection Amount | Comments | Month of Actual Collection | Collection call status
SF_CR_1108 | SF | FY 25-26 | Ivanti Technology | PMSF_0546 | Ivanti Technology India Pvt. Ltd. | 9908304 |  | 35% | Signing of MoU | Advance | 2025-09-01 | 3467906 | 2025-09-01 | 2025-09-18 | 3467906 | SFPRJ26_000082 | 2025-09-01 | 2025-09-01 | Sep'25 | Received | 2025-09-26 | 3467906 |  | Sep-2025
SF_CR_1108 | SF | FY 25-26 | Ivanti Technology | PMSF_0546 | Ivanti Technology India Pvt. Ltd. |  |  | 35% | Batch 1 training & assessment completed & placement started, B2 training ongoing | 2nd Installment | 2025-11-01 | 3467906.4 | 2025-12-01 |  |  |  | 2025-12-01 | 2026-01-01 | Jan'26 | To be billed |  |  |  |  | Dec-week 1 FRL raising
SF_CR_1108 | SF | FY 25-26 | Ivanti Technology | PMSF_0546 | Ivanti Technology India Pvt. Ltd. |  |  | 30% | B2 placements completed, B3 placement process initiated, B4 launched | 3rd Installment | 2026-01-01 | 2972491.2 | 2026-01-01 |  |  |  | 2026-02-01 | 2026-02-01 | Feb'26 | To be billed