## Document Version
Project ID | yet to create
Project Name | yet to create
Document Version | 1.0
Date of Creation | 2025-11-20
Last Updated | 2025-11-20

## Project Overview
Project overview
Field | Details
Project Title | Provide Government Welfare Schemes Support to Fabricators at multiple locations across India
Brief Project Description | The program aims to create awareness on selected Government Social Security Schemes and support the enrolment of participants (fabricators) into a minimum of two schemes each. Sambhav Foundation will conduct 20 camps across Tamil Nadu and Kerala, reaching at least 600 participants. Each camp will include an awareness session using a customized and translated presentation, participant support for enrolment, data capture, and issuance of participation certificates to those enrolled. Mobilization, food, and venue infrastructure will be provided by Tata Bluescope.
Project Funder | Tata Bluescope Steel Pvt. Ltd.
Project Entity | Sambhav Foundation
MOU Effective Start Date | 2025-10-01
MOU End Date | 2026-03-01
Project Start Date | 2025-11-23
Project End Date | 2026-03-31
Deployment Region | Tamil Nadu, Kerela
Intervention | - Conduct 20 on-ground Social Security Awareness Camps in Tamil Nadu and Kerala - Deliver awareness sessions on selected schemes using customized and simplified presentations - Support enrolment of each participant into at least two eligible schemes - Provide a dedicated helpline/contact number for post-camp clarifications
Tata Bluescope responsibilities | - Mobilize participants for the camp - Arrange for infra and other arrangements for camp - Arrange for refreshments during camp - Ensure branding at the camp
Expected Outcomes | - Increased awareness among participants on key Government Social Security Schemes - Improved access to and utilization of social protection schemes - Successful enrolment of minimum 600 participants into at least two schemes each - Strengthened understanding of entitlements and documentation requirements - Increased readiness of participants to access future welfare schemes independently
Key Deliverables | - 20 Awareness Camps conducted across Tamil Nadu & Kerala
- Awareness presentation developed in English and translated into Hindi, Malayalam, and Tamil
- Beneficiary Data Capture Format (digital/IT platform) developed
- Participation Certificates designed, printed, and distributed
- Beneficiary MIS including attendance and enrolment status
- Post-camp awareness survey and analysis report
- Dedicated helpline number operational for participant queries
- Final consolidated impact summary at end of program
Monitoring and Reporting | - Daily camp-level MIS: attendance, scheme enrolment, data completeness
- 600 beneficiary data
- Post-camp awareness survey administration and data analysis
-Submission of consolidated donor report with impact insights and enrolment outcomes
- Documentation of queries received through dedicated helpline
Overall Objective | To enable fabricator-workers to access Government Social Security Schemes by increasing awareness and facilitating enrolment, thereby enhancing their financial security and social protection coverag

## HR Sheet
Role | No. of positions | Direct/Indirect | Full time/Shared | Description | Responsibilities | Status of deployment | Name of the employee deployed
Project Coordinator cum Facilitator (2) | 2 | Direct | Shared - on camp basis | Frontline staff conducting awareness sessions, supporting scheme enrolment, and managing camp execution. | - Conduct awareness sessions using presentation - Explain scheme details to participants - Support enrolment into minimum two schemes - Collect & verify beneficiary data in IT platform - Manage camp flow and logistics coordination - Distribute handouts and participation certificates - Assist with post-camp survey• Submit daily camp MIS
Operations Supervisor/TM | 1 | Indirect | Shared | Oversees operational planning, logistics, resource deployment, and ensures smooth execution of all camps. | - Coordinate with client on infra, food, mobilization - Deploy facilitators & ensure availability of laptop/projector - Manage travel logistics - Resolve on-ground issues - Review daily MIS from coordinators - Ensure timely dispatch of certificates & materials
Project Manager | 1 | Indirect | Shared | Provides project oversight, donor coordination, quality assurance, and monitors timelines & deliverables. | - Liaise with Tata Bluescope - Monitor camp progress vs plan - Ensure data quality across camps - Approve MIS and oversee reporting - Track financials aligned with cost sheet - Support in resolving escalations
MIS & Beneficiary Support Executive | 1 | Direct | Shared - on camp basis | Manages beneficiary data, MIS generation, helpline queries, and IT platform entries. | - Maintain beneficiary database - Monitor daily data uploads - Ensure data completeness and accuracy - Manage dedicated helpline number - Track and document beneficiary queries (informational only) - Prepare weekly/monthly MIS summaries• Coordinate with IT team on issues
Post-Survey Analysis & Reporting - Impact report personnel | 1 | Indirect | Shared | Handles analysis of post-camp survey data and prepares impact reports. | - Design survey analysis plan - Clean and analyse survey data - Prepare camp-wise survey reports - Consolidate program-level impact summary - Support PM in final donor reporting

## Activity Sheet
Milestone / Cost Head | Activity | Evidence Requirement | Responsibility | Start Date | End Date | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Status of completion | Comments
Manpower (Team Lead, Expert, Operations Incharge) | - Assign project manager, operations supervisor, coordinators, MIS person | Deployment mail | HR Team | 2025-11-01 | 2025-11-01
Manpower (Team Lead, Expert, Operations Incharge) | - Develop month-wise deployment plan - Ensure attendance, travel, reporting compliance - Oversight of quality, MIS, donor updates | - Monthly attendance sheet - Timesheets- deployment plan - Salary/consultant invoices | PM, TM | 2025-11-01 | 2025-11-01
Travel of Staff | - plan travel for coordinators & team per camp- Local transport arrangements | - Travel bills (tickets, fuel, local transport)- Approved travel plan (email/WhatsApp proof) | TM | 2025-11-01 | 2026-03-01
Content Customization / Scheme Details Handouts & Leaflets | - Prepare awareness presentation on schemes - Translate into Hindi, Malayalam, Tamil - Content QA & approval | - Final PPT in 3 languages - Translation files - Printing bills - Sample printed copies - Content approval email | Content Development Team, PM | 2025-11-01 | 2025-11-01
Printing & Stationery & Training Material | - Pring forms, any other material required for training - Procure stationery (pens, registers, markers) | - Printing invoices - Stationery invoices - Distribution log / material issuance register | Admin Team, TM | 2025-11-01 | 2026-03-01
Participant Certificates | - Coordinate with martketing team for certificate design - Marketing team to design certificate and share for donor approval - Take donor approval on final certificate design | - Certificate design file - Donor approval mail | PM | 2025-11-01 | 2025-11-01
Participant Certificates | - Print certificates - Distribute certificate to all enrolled participants during camp - Take certificate received acknowledgement | - Printing bill - Certificate acknowledgement letter | Admin Team, Project Coordinators | 2025-11-01 | 2026-03-01
Documentation & Consultation (Through Phone) | - Set up dedicated helpline number - Attend participant calls post-camp - Record type of queries for documentation | - Call log / query register - Phone bill - Documentation summary of queries | MIS & Beneficiary Support Executive | 2025-11-01 | 2026-03-01
Laptop, Projector & Internet on Rent | - Arrange 1 laptop and projector for all 20 camps - Ensure backup internet/dongle availability - Coordinate renting and maintenance | - Rental invoices- Material issue/return register - Photographs of equipment at camps | Admin Team, TM | 2025-11-01 | 2026-03-01
Post-Awareness Survey, Analysis & Reporting | - Coordinate and prepare post awareness survey questionnaire - Share the questionnaire with the project coordinators with instructions to get the response of all participants | - Email communication - Survey form | PM, Impact Team | 2025-11-01 | 2025-11-01
Post-Awareness Survey, Analysis & Reporting | - Conduct post-awareness survey at camp - Share the survey data with the impact assessment team for analysis - Impact Team to prepare survey reports - Impact Team to prepare end of project impact report | - Survey forms (digital or paper) - Data sheets - Survey analysis report - Impact report | Project Coordinators, Impact Team | 2025-11-01 | 2026-03-01
IT Platform to Capture Beneficiary Data | - Develop data template - Capture beneficiary details at camp - Ensure accuracy and validation - Maintain backend access and data security | - Beneficiary database export - IT platform invoice - Screenshots of data entries - Data validation log | MIS & Beneficiary Support Executive | 2025-11-01 | 2026-03-01
Training | - Conduct 20 awareness sessions - Manage participant flow & seating - Ensure smooth delivery using PPT - Maintain attendance & enrolment support | - Attendance sheets - Photos of sessions - Session report per camp | Project Coordinators | 2025-11-01 | 2026-03-01
Documentation & Reporting | - Share the list of documents required for each scheme with donor POC which can be shared with participants during mobilization - Compile camp-wise MIS - Prepare monthly progress updates - Final consolidated report for donor | - Camp MIS - Monthly reports - Final report (PDF) | Project Manager, MIS Executive | 2025-11-01 | 2026-03-01
Note on A15: Author: not a cost head
Note on A16: Author: not a cost head

## Capex Specifications
Item | Nos. per camp | Details
Laptop | 1 | to be taken on rent per camp
Projector | 1 | to be taken on rent per camp
* Total 20 camps to be conducted

## Marketing
Type | Details | Execution Methods | Evidence Required
B2C | Certificate Design | - Create clean, professional certificate template aligned to program branding - Ensure print-ready format (PDF + editable version) | - Certificate design file - Donor approval mail
B2B | Social Media Posts | - Draft posts showcasing program highlights (camp execution, impact numbers, participant stories) - Use approved branding, templates, and disclosure guidelines - Coordinate with partner (Tata Bluescope) for tagging/approvals - Schedule posts across platforms (LinkedIn, Instagram, Facebook) | - Final post designs and captions - Approval email/screenshots from internal team + Tata Bluescope - Social media URLs of published posts - Screenshot of post insights (reach, engagement, likes/comments)

## Key Partners
* Key Partners are the essential external and internal stakeholders who contribute specialized expertise, resources, approvals, or operational support required for successful implementation of the project. They play a critical role in ensuring that each stage—from planning and procurement to installation, community engagement, and long-term maintenance—is executed effectively, on time, and in compliance with quality and safety standards.
Partner Type | Description | Partner Name
Translation Partner | Translates awareness content and presentations into Hindi, Malayalam, and Tamil, ensuring accuracy and simplicity for participants.
Camp Venue Partners | Offer location where camp is conducted; ensure power, seating, and basic infrastructure required for awareness sessions. | Locations facilitated through Tata Bluescope

## Formats
Format Name | Description | Responsibility
Attendance Sheet format | for all the participants who attended the awareness session | Attached
Beneficiary details tracker format | for capturing the details of the participants who enrolled for the schemes | Attached
Certificate Design | Certificate soft copy for printing | PM, Marketing Team
Certificate acknowledgement format | Form where participant's acknowledgement can taken after providing the certificate | Attached
Post Awareness Survey form | Survey form for taking participant's knowledge and awareness level post the awareness session | PM, Impact Assessment Team

## Key Metrics
Metric Description | Target | Internal / Donor Reporting
Number of camps conducted | 20 camps | Donor & Internal
Total participants reached | 600 participants | Donor & Internal
Average participation per camp | ~60-80 participants per camp | Donor & Internal
No. of participants enrolled (out of attendees) | min. 30 (out of the total attendees attending the session, minimum 30 should be enrolled in at least 2 schemes) | Donor & Internal
Participants enrolled into minimum two schemes | 600 beneficiaries × 2 schemes each (1,200+ scheme enrolments) | Donor & Internal
Awareness sessions delivered using approved presentation | 20 sessions | Internal
Availability of translated presentations (Hindi, Malayalam, Tamil) | 100% | Internal
Enrolmment certificates distributed | 600 certificates | Donor & Internal
Beneficiary data captured | 100% data capture for all attendees | Donor & Internal
Data accuracy & completeness rate | 95%+ accurate entries | Internal
Post-awareness surveys completed | 90% of total attendees | Donor & Internal
MIS submission timelines | After each camp | Donor
Helpline query resolution | Query log maintained; 100% queries responded | Internal
Timely printing & material readiness per camp | 100% materials delivered before each camp | Internal
Camp documentation (photos, attendance, MIS) | 20 completed sets | Internal & Donor

## Impact framework
DKSB Element | Impact Indicator | What It Measures | Data Source
Data | % of Participants Successfully Enrolled into Minimum Two Schemes | Actual uptake of schemes, showing improved access and ability to navigate enrolment. | Beneficiary & Enrolment Data
Data | Average Number of Schemes Enrolled per Participant | Depth of scheme utilisation and participant initiative to access more benefits. | Enrolment records
Knowledge | % Increase in Participant Awareness Levels | Improvement in understanding of scheme benefits, eligibility, and documentation. | Post-camp awareness survey
Knowledge | % of Participants Reporting Clear Understanding of Application Steps & Documentation | Practical clarity on “how to apply” → improves future independent access. | Post-camp survey
Skills | % of Participants Who Report They Can Explain Schemes to Others | Confidence to disseminate awareness → proxy for sustainability & internalisation. | Post-camp survey

## List of Schemes to be covered
Scheme Name | Scheme Description | Documents Required
Pradhan Mantri Jeevan Jyoti Beema Yojana | This is an insurance scheme offering life insurance cover of ₹ 200000 to people in the age group 18-50 years, for death due to any reason (accidental/natural) for a premium of ₹ 436 per year. It is a one year (1st June to 31st May) cover, renewable from year to year. | - Aadhaar card - Bank account details - Nominee information - Consent form
Pradhan Mantri Suraksha Bima Yojana | This is an accidental Insurance scheme for people in the age group 18-70 years.It provides insurance of ₹ 200000 in case of death/complete Disability and ₹ 100000 in case of partial disability, at a premium of ₹ 20 (auto-debited) from policy holders account (linked with Aadhar). It is a one year (1st June to 31st July) cover, renewable from year to year. | - Aadhaar card - Bank account details - Nominee information - Consent form
Atal Pension Yojana | The scheme provides a guaranteed pension of up to 5,000/- per month after the age of 60 years depending on the contributions by the subscribers. Any Citizen of India in the age group of 18 - 40 years can apply for the scheme | - Aadhaar card - Bank account details - Mobile number - APY registration form
Pradhan Mantri Shram Yogi Mandhan Yojana | This scheme provides a monthly old age pension of Rs. 3000/- to Unorganized Workers after attaining the age of 60 years. The applicants between the age group of 18 to 40 years will have to make monthly contributions ranging between Rs 55 to Rs 200 per month till they attain the age of 60. | - Aadhaar card - Savings/Jan Dhan bank account details - Mobile number - Self-declaration of unorganized worker status
Ayushman Bharat - Pradhan Mantri Jan Arogya Yojana | A scheme providing free-of-cost health insurance to over 55 crore beneficiaries. It covers up to Rs. 5 lakh per family per year for secondary and tertiary care hospitalization. | - Aadhaar card - Ration Card / Family ID (optional but helpful) - Mobile number - SECC-based eligibility verification - Ayushman Card (can be generated at Common Service Centre)
Income Certificate | This document helps as a proof of belonging to economically vulnerable category and is required to be for most of the welfare schemes applications | - Aadhaar Card - Address Proof (Ration card / Voter ID / Electricity bill) - Recent salary slip / Income proof / Self-declaration - Passport-size photo - PAN card (optional)
Sukanya Samriddhi Account Scheme | This is an investment scheme where an account can be opened in the name of a girl child below 10 years of age. Contribution has to be paid for 15 years of opening an account and the same will mature after 21 years. The scheme provides assured interest of 8.2% per annum. Premature withdrawals are allowed for girl's higher education | - Girl child’s Birth Certificate - Photograph of child and parent - Account opening form. - Parent’s/Guardian’s Aadhaar & Address Proof